## Entities
Entity_ID | Entity_Name | Category | Description | Owner | Criticality
ENT_ENTERPRISE | Enterprise | Organization | Complete organizational context spanning all Business Units and portfolios. | Executive Management | Critical
ENT_PORTFOLIO | Portfolio | Organization | Collection of projects rolled up for executive oversight. | PMO / Executive | High
ENT_BUSINESS_UNIT | Business Unit | Organization | Organizational entity that owns and executes a project; one primary BU per project. | Business Head | Critical
ENT_PLANT | Plant | Organization | SAP organizational identifier for the operating location of transactions. | Capital Finance M&C | Medium
ENT_PROJECT | Project | Core Business Object | Primary investment entity approved via a CAPEX NFA. | Project Manager / CPO | Critical
ENT_PACKAGE | Package | Core Business Object | Primary execution unit; Engineering/Procurement/Construction managed package-wise. | Package Owner | Critical
ENT_WBS | Work Breakdown Structure | Core Business Object | Hierarchical decomposition of scope; standardized to enterprise levels; dynamic link to Package. | Scheduler / Planning | High
ENT_ACTIVITY | Activity | Core Business Object | Smallest executable unit of work; convergence point of physical progress. | Scheduler / Package Owner | Critical
ENT_MILESTONE | Milestone | Business Event Object | Significant business event (NFA Approved, RFC Released, PO Issued, COD). | Project Manager | High
ENT_BASELINE | Schedule Baseline | Business Artifact | Approved Primavera schedule serving as the official reporting reference. | Planning / PMAT | Critical
ENT_CAPEX_NFA | CAPEX NFA | Governance Artifact | Primary approval document authorizing the capital investment. | Business Initiator | Critical
ENT_AMENDMENT_NFA | Amendment NFA | Governance Artifact | Revises an approved CAPEX investment (budget/scope/timeline). | Business Initiator | High
ENT_COMMERCIAL_NFA | Commercial NFA | Governance Artifact | Approval governing procurement decisions; authorizes PO/SO issuance. | Procurement | Critical
ENT_CAPEX_PLAN | CAPEX Plan | Financial Artifact | Month-wise approved CAPEX distribution (Hard/Soft/Land/Contingency). | Business Initiator / Finance | High
ENT_AOP | Annual Operating Plan | Financial Artifact | Annual CAPEX and Cash Flow plan; annual financial baseline. | Finance | High
ENT_PRECON_ACTIVITY | Pre-Construction Activity | Business Object | Readiness activity tracked in PreCon360 (land, statutory, utility). | Business Owner (PreCon) | High
ENT_STATUTORY_APPROVAL | Statutory Approval | Governance Object | Regulatory approval decomposed into structured approval hierarchies. | Corporate Affairs / Legal | High
ENT_LAND | Land Status | Business Object | Land readiness tracked as Required / Acquired / Balance. | Land Team | High
ENT_MDL | Master Deliverable List | Engineering Artifact | Approved engineering baseline defining all expected package deliverables. | Engineering Vendor + Owner Engg | Critical
ENT_ENGG_DOC | Engineering Document | Core Business Object | Controlled engineering deliverable progressing through review to RFC/GFC. | Engineering Team | Critical
ENT_REVISION | Document Revision | Business Artifact | Controlled version of an engineering document with independent review/approval history. | Document Controller | Medium
ENT_TBER | Technical Bid Evaluation Report | Procurement Artifact | Engineering evaluation ranking vendor technical proposals (T1, T2). | Engineering | High
ENT_PR | Purchase Request | Procurement Artifact | Formal request initiating procurement; reserves project budget. | Project / Procurement | High
ENT_RFP | Request for Proposal | Procurement Artifact | Document inviting approved vendors to submit technical & commercial proposals. | Procurement | Medium
ENT_PO | Purchase Order | Procurement Artifact | Contractual document authorizing material procurement; SoR in SAP. | Procurement | Critical
ENT_SO | Service Order | Procurement Artifact | Contractual document authorizing service procurement. | Procurement | High
ENT_INTERNAL_ESTIMATE | Internal Estimate | Procurement Artifact | Confidential internal cost benchmark used during commercial evaluation. | Estimation Team | Medium
ENT_VENDOR | Vendor | Core Business Object | External organization supplying engineering/materials/equipment/services. | Procurement / Vendor Mgmt | Critical
ENT_CONTRACTOR | Contractor | Core Business Object | Vendor responsible for physical construction execution. | Package Owner | High
ENT_CONSULTANT | Consultant | Core Business Object | Owner's Engineer performing design, validation and review. | Engineering Team | Medium
ENT_MATERIAL | Material | Core Business Object | Physical resource consumed during execution; may be Free Issue Material. | Material Management | High
ENT_GRN | Goods Receipt Note | Financial Artifact | SAP transaction confirming material receipt; basis for CAPEX recognition. | Stores / Finance | Critical
ENT_SES | Service Entry Sheet | Financial Artifact | SAP transaction confirming service acceptance; basis for CAPEX recognition. | Finance / Project | Critical
ENT_INVOICE | Invoice | Financial Artifact | Vendor payment request processed after GRN/SES. | Finance | Medium
ENT_INVENTORY | Inventory | Business Object | Stock held after GRN and before construction consumption. | Stores / Material Management | Medium
ENT_RESOURCE | Execution Resource | Core Business Object (Abstract) | Generic parent for consumable execution resources. | Project Team | High
ENT_HUMAN_RESOURCE | Human Resource (Manpower) | Business Object (Subtype) | Manpower deployed for execution and productivity measurement. | Contractor / Site Team | High
ENT_MATERIAL_RESOURCE | Material Resource | Business Object (Subtype) | Materials as an execution resource for construction. | Material Management | Medium
ENT_EQUIPMENT_RESOURCE | Equipment Resource | Business Object (Subtype) | Machinery/equipment used in construction execution. | Site Team | Medium
ENT_DPR | Daily Progress Report | Construction Artifact | Daily site execution record prepared by site team/contractor. | Site Team / Package Owner | Medium
ENT_WPR | Weekly Progress Report | Construction Artifact | Weekly consolidation feeding Primavera and dashboards. | Package Owner | Medium
ENT_NCR | Non-Conformance Report | Quality Object | Quality record raised on non-conforming material/workmanship. | Quality Team | High
ENT_SAFETY_EVENT | Safety Event | Safety Object | Safety observation/near-miss/incident/LTI/fatality record. | Safety Team | High
ENT_RISK | Risk | Governance Object | Potential future event with probability & impact tracked in a Risk Register. | Risk Owner / PMO | Medium
ENT_ISSUE | Issue | Governance Object | Realized problem tracked in an Issue Register. | Project Manager | Medium
ENT_PACKAGING_STRATEGY | Packaging Strategy | Governance Artifact | Governing artifact defining how scope is divided into packages (EPC, E+S). | Project / Engineering | High
ENT_PROJECT_DEFINITION | SAP Project Definition | System Business Object | SAP object organizing WBS and financial transactions for a project. | Capital Finance M&C | High
ENT_DOA | Delegation of Authority | Governance Object | Approval-authority framework by value/BU (a.k.a. TOA). | Corporate Governance | Critical
ENT_DASHBOARD | Enterprise Dashboard | Analytical Object | Curated analytical view consuming Data Lake datasets; supports drill-down. | PMO / Business Function | Medium
ENT_PHYSICAL_PROGRESS | Physical Progress | Analytical Object | Derived metric of executed work (from Primavera activities). | Planning / PMO | High
ENT_FINANCIAL_PROGRESS | Financial Progress | Analytical Object | Derived metric of CAPEX incurred vs approved plan (AOP / project CAPEX). | Finance / PMO | High
ENT_CAPEX | CAPEX | Analytical Object | Capitalized investment recognized on GRN/SES. | Finance | High
ENT_CASH_FLOW | Cash Flow | Analytical Object | Actual cash movement to vendors; distinct from CAPEX. | Finance | High
ENT_CRITICAL_PATH | Critical Path | Analytical Object | Activity chain determining project completion. | Planning | High
ENT_SYS_CAPEXPERT | CapExpert | System | CAPEX governance & project initiation system. | Digital / IT | Medium
ENT_SYS_PRIMAVERA | Primavera P6 | System | Planning & schedule management system of record. | Digital / IT | Medium
ENT_SYS_PRECON360 | PreCon360 | System | Pre-Construction readiness system of record. | Digital / IT | Medium
ENT_SYS_AUTODESK | Autodesk CDE | System | Engineering document management system of record. | Digital / IT | Medium
ENT_SYS_ARIBA | SAP Ariba | System | Procurement lifecycle & Commercial NFA system. | Digital / IT | Medium
ENT_SYS_SAP | SAP ERP | System | Transactional SoR for PR/PO/SO/GRN/SES/finance/inventory. | Digital / IT | Medium
ENT_SYS_DATALAKE | Enterprise Data Lake | System | Enterprise integration & analytical repository. | Digital / Analytics | Medium
ENT_SYS_DASHBOARDS | Enterprise Dashboards | System | BI & executive reporting layer. | Digital / Analytics | Medium

## Relationships
From | Relationship | To | Cardinality | Description
ENT_BUSINESS_UNIT | OWNS | ENT_PROJECT | 1:N | One BU owns each project (BR-003).
ENT_PROJECT | BELONGS_TO | ENT_BUSINESS_UNIT | N:1 | Project belongs to exactly one owning BU.
ENT_PROJECT | GOVERNED_BY | ENT_CAPEX_NFA | 1:1 | Project authorized by an approved CAPEX NFA (BR-002).
ENT_AMENDMENT_NFA | SUPERSEDES | ENT_CAPEX_NFA | N:1 | Amendment revises original CAPEX (parent link Inferred - not system-maintained).
ENT_CAPEX_NFA | APPROVED_BY | ENT_DOA | N:1 | Approval path determined by Delegation of Authority.
ENT_CAPEX_NFA | CONTAINS | ENT_CAPEX_PLAN | 1:1 | NFA carries the month-wise CAPEX plan.
ENT_PROJECT | CONTAINS | ENT_PACKAGE | 1:N | Project decomposed into packages.
ENT_PACKAGE | BELONGS_TO | ENT_PROJECT | N:1 | Package belongs to one project.
ENT_PACKAGE | GOVERNED_BY | ENT_PACKAGING_STRATEGY | N:1 | Packaging Strategy defines package scope/type.
ENT_PROJECT | CONTAINS | ENT_WBS | 1:N | Project WBS hierarchy.
ENT_PACKAGE | REFERENCES | ENT_WBS | N:M | Dynamic Package-WBS mapping (not fixed level).
ENT_WBS | CONTAINS | ENT_ACTIVITY | 1:N | Activities organized under WBS.
ENT_BASELINE | CONTAINS | ENT_ACTIVITY | 1:N | Approved baseline schedule of activities.
ENT_ACTIVITY | DEPENDS_ON | ENT_ACTIVITY | N:M | Predecessor-successor logic (BR-009).
ENT_CRITICAL_PATH | DERIVED_FROM | ENT_ACTIVITY | 1:N | Critical Path computed from activity network.
ENT_PROJECT | CONTAINS | ENT_MILESTONE | 1:N | Project milestone catalog.
ENT_PROJECT | MONITORED_BY | ENT_PRECON_ACTIVITY | 1:N | Readiness tracked via PreCon activities.
ENT_PRECON_ACTIVITY | CONTAINS | ENT_STATUTORY_APPROVAL | 1:N | Statutory approvals as structured hierarchies (BR-018).
ENT_PRECON_ACTIVITY | REFERENCES | ENT_LAND | 1:1 | Land activities track Required/Acquired/Balance (BR-017).
ENT_PACKAGE | GOVERNED_BY | ENT_MDL | 1:1 | Each engineering package maintains an MDL (BR-019).
ENT_MDL | CONTAINS | ENT_ENGG_DOC | 1:N | MDL enumerates all expected documents.
ENT_ENGG_DOC | BELONGS_TO | ENT_PACKAGE | N:1 | Every engineering document belongs to one package.
ENT_ENGG_DOC | CONTAINS | ENT_REVISION | 1:N | Document maintains revision history (BR-020/GBR-009).
ENT_CONSULTANT | REVIEWS | ENT_ENGG_DOC | N:M | Consultant/owner review cycles.
ENT_VENDOR | GENERATED_FROM | ENT_MDL | N:1 | Engineering vendor produces MDL deliverables (co-owned).
ENT_ACTIVITY | DEPENDS_ON | ENT_ENGG_DOC | N:M | Construction activity depends on RFC/GFC document (BR-032).
ENT_PR | GENERATED_FROM | ENT_PACKAGE | N:1 | One PR per package (best practice).
ENT_PR | GENERATED_FROM | ENT_RFP | 1:1 | Each PR yields one RFP (BR-026).
ENT_RFP | AWARDED_TO | ENT_VENDOR | N:1 | RFP awarded to selected vendor.
ENT_TBER | REFERENCES | ENT_RFP | 1:1 | Technical evaluation of bids for an RFP.
ENT_COMMERCIAL_NFA | REFERENCES | ENT_INTERNAL_ESTIMATE | 1:1 | Commercial NFA benchmarks against internal estimate.
ENT_COMMERCIAL_NFA | APPROVED_BY | ENT_DOA | N:1 | Commercial approval per DOA (BR-030).
ENT_PO | GENERATED_FROM | ENT_COMMERCIAL_NFA | N:1 | PO issued after Commercial NFA approval.
ENT_SO | GENERATED_FROM | ENT_COMMERCIAL_NFA | N:1 | SO issued after Commercial NFA approval.
ENT_PO | AWARDED_TO | ENT_VENDOR | N:1 | PO awarded to a vendor.
ENT_PO | CONTAINS | ENT_MATERIAL | 1:N | PO line items for materials.
ENT_MATERIAL | GENERATED_FROM | ENT_GRN | 1:N | GRN confirms material receipt.
ENT_GRN | STORED_IN | ENT_SYS_SAP | N:1 | GRN transaction in SAP.
ENT_SES | GENERATED_FROM | ENT_SO | N:1 | SES confirms service acceptance under an SO.
ENT_CAPEX | DERIVED_FROM | ENT_GRN | N:M | CAPEX recognized on GRN (BR-039).
ENT_CAPEX | DERIVED_FROM | ENT_SES | N:M | CAPEX recognized on SES (BR-039).
ENT_INVOICE | GENERATED_FROM | ENT_GRN | N:1 | Invoice processed after GRN/SES.
ENT_CASH_FLOW | DERIVED_FROM | ENT_INVOICE | N:M | Cash Flow from vendor payments/advances.
ENT_MATERIAL | STORED_IN | ENT_INVENTORY | N:1 | Received material held in inventory.
ENT_CONTRACTOR | EXECUTED_BY | ENT_ACTIVITY | N:M | Contractor executes construction activities.
ENT_ACTIVITY | CONTAINS | ENT_DPR | 1:N | Daily execution captured per activity.
ENT_DPR | SUPPORTS | ENT_WPR | N:1 | DPRs consolidated into WPR.
ENT_WPR | SUPPORTS | ENT_ACTIVITY | N:M | Validated WPR updates Primavera progress.
ENT_ACTIVITY | EXECUTED_BY | ENT_RESOURCE | N:M | Activities consume execution resources.
ENT_RESOURCE | CONTAINS | ENT_HUMAN_RESOURCE | 1:N | Subtype: manpower (inheritance).
ENT_RESOURCE | CONTAINS | ENT_MATERIAL_RESOURCE | 1:N | Subtype: material resource.
ENT_RESOURCE | CONTAINS | ENT_EQUIPMENT_RESOURCE | 1:N | Subtype: equipment.
ENT_PHYSICAL_PROGRESS | MEASURED_BY | ENT_ACTIVITY | 1:N | Physical progress derived from activity completion (BR-037).
ENT_FINANCIAL_PROGRESS | MEASURED_BY | ENT_CAPEX | 1:1 | Financial progress from CAPEX vs baseline/AOP.
ENT_CAPEX | REFERENCES | ENT_AOP | N:1 | Annual financial progress measured vs AOP (BR-040).
ENT_NCR | REFERENCES | ENT_MATERIAL | N:M | NCR raised on non-conforming material/workmanship.
ENT_NCR | BLOCKS | ENT_ACTIVITY | N:M | Quality non-conformance can block activity acceptance (Inferred).
ENT_SAFETY_EVENT | REFERENCES | ENT_ACTIVITY | N:M | Safety events arise from construction activities.
ENT_RISK | REFERENCES | ENT_PROJECT | N:1 | Project risk register.
ENT_VENDOR | MONITORED_BY | ENT_NCR | N:M | Vendor quality performance monitored via NCRs.
ENT_PROJECT | REFERENCES | ENT_PROJECT_DEFINITION | 1:N | Project mapped to SAP Project Definition (canonical ID resolution needed).
ENT_DASHBOARD | DERIVED_FROM | ENT_SYS_DATALAKE | N:1 | Dashboards consume Data Lake datasets.
ENT_ENGG_DOC | STORED_IN | ENT_SYS_AUTODESK | N:1 | Engineering docs SoR in Autodesk.
ENT_BASELINE | STORED_IN | ENT_SYS_PRIMAVERA | N:1 | Schedule baseline SoR in Primavera.
ENT_CAPEX_NFA | STORED_IN | ENT_SYS_CAPEXPERT | N:1 | CAPEX NFA SoR in CapExpert.
ENT_COMMERCIAL_NFA | STORED_IN | ENT_SYS_ARIBA | N:1 | Commercial NFA SoR in Ariba.
ENT_PO | STORED_IN | ENT_SYS_SAP | N:1 | PO SoR in SAP (BR-028).

## Processes
Process | Step_No | Step | Next_Step | Owner | Description
Project Initiation | 1 | Identify Business Opportunity | 2 | Business Development | Trigger is BU-specific; outside enterprise standardization.
Project Initiation | 2 | Prepare CAPEX NFA & Supporting Docs | 3 | Business Initiator | Captures project, financial, CAPEX plan & pre-con baseline.
Project Initiation | 3 | Main Approval Flow | 4 (if > threshold) / 5 | DOA Approvers | Mandatory enterprise approval per DOA.
Project Initiation | 4 | Top Approval Flow | 5 | Governance Team / Chairman | Supplements Main Flow for high-value projects.
Project Initiation | 5 | Project Approved | -> Planning | Project Manager / CPO | Project formally recognized on NFA approval.
CAPEX NFA Approval | 1 | NFA Preparation | 2 | Business Initiator | Financial models, feasibility, justifications attached.
CAPEX NFA Approval | 2 | Determine Approval Path (DOA) | 3 | Governance | Path depends on BU + CAPEX value.
CAPEX NFA Approval | 3 | Multi-stage Approval | 4 | DOA Approvers | Full matrix Needs SME Validation (KB-001).
CAPEX NFA Approval | 4 | Approval Complete | -> Planning | Business Initiator | Governance history retained.
Planning & Baseline | 1 | Create Primavera Project | 2 | Scheduler | Dedicated schedule per project.
Planning & Baseline | 2 | Create WBS | 3 | Scheduler | Standardized to enterprise levels (L2/L3).
Planning & Baseline | 3 | Create Activities & Assign Logic | 4 | Scheduler | Predecessor/successor network.
Planning & Baseline | 4 | Assign Resources | 5 | Planning | Labour/machinery/materials.
Planning & Baseline | 5 | Create Baseline | 6 | Planning | One official enterprise baseline.
Planning & Baseline | 6 | Baseline Approval | -> Execution | PMAT / CPMAT | Governance varies by BU (workflow KB-006).
Pre-Construction | 1 | Import Pre-Con Baseline to PreCon360 | 2 | Business Owner | Checklist from initiation expanded.
Pre-Construction | 2 | Update Readiness & Ownership | 3 | Pending-With Team | One active owner at a time (BR-015).
Pre-Construction | 3 | Upload Supporting Docs | 4 | Business Owner | Managed via Autodesk.
Pre-Construction | 4 | Readiness Monitoring | -> Construction Ready | PMO | Complete when all applicable activities done.
Engineering | 1 | Define Packaging Strategy | 2 | Project / Engineering | Governs vendor, procurement, construction.
Engineering | 2 | Vendor Selection & Onboarding | 3 | Engineering / Procurement | Precedes MDL.
Engineering | 3 | Establish MDL | 4 | Engg Vendor + Owner Engg | Jointly agreed engineering baseline (BR-024).
Engineering | 4 | Produce & Submit Documents | 5 | Engineering Vendor | Document-level lifecycle.
Engineering | 5 | Review (Consultant/Owner) & Revise | 6 | Consultant / Owner Engg | Consultant step may be bypassed.
Engineering | 6 | Approve & Release RFC/GFC | -> Construction | Engineering Team | Release at document level (BR-022).
Procurement | 1 | SAP Project Preparation | 2 | Capital Finance M&C | Project Definition, Plant/Company Code, WBS.
Procurement | 2 | Create Purchase Request | 3 | Project / Procurement | Reserves budget; one package per PR.
Procurement | 3 | Issue RFP | 4 | Procurement | Includes engineering tech specs.
Procurement | 4 | Technical Clarification & Bid | 5 | Engineering / Vendors | Requirements frozen after clarification.
Procurement | 5 | Technical Bid Evaluation (TBER) | 6 | Engineering | Establishes T1/T2 before commercials (BR-027).
Commercial Approval | 1 | Commercial Evaluation / Reverse Auction | 2 | Procurement | Price comparison & negotiation.
Commercial Approval | 2 | Prepare Commercial NFA | 3 | Procurement | Includes internal estimate benchmark.
Commercial Approval | 3 | Commercial NFA Approval (DOA) | 4 | DOA Approvers | ~13-14 checkpoints (Needs SME Validation, KB-002).
Commercial Approval | 4 | Issue PO / SO in SAP | -> Material Delivery | Procurement | Procurement complete on issuance (BR-029).
Material Delivery & Receipt | 1 | Material Delivery | 2 | Vendor | Against PO schedule.
Material Delivery & Receipt | 2 | Goods Receipt (GRN) | 3 | Stores | Triggers CAPEX recognition.
Material Delivery & Receipt | 3 | Inventory / Issue to Contractor | 4 | Material Management | FIM issued to contractor.
Material Delivery & Receipt | 4 | Consumption & Reconciliation | -> Construction | Material Management | Reconciliation esp. for FIM (BR-035).
Construction | 1 | Verify Construction Readiness | 2 | Package Owner | RFC/GFC + statutory + land + material.
Construction | 2 | Mobilization | 3 | Contractor | Manpower/equipment deployment.
Construction | 3 | Daily Execution & DPR | 4 | Site Team / Contractor | Quantities, manpower, constraints.
Construction | 4 | Weekly Validation (WPR) -> Primavera | 5 | Package Owner | Validated progress updates schedule.
Construction | 5 | Activity Completion | -> Progress / Commissioning | Package Owner | Physical completion only (BR-036).
Progress Measurement | 1 | Collect DPR/WPR & Primavera Updates | 2 | Planning | Physical progress source.
Progress Measurement | 2 | Compute Physical vs Planned | 3 | Planning / PMO | Schedule variance, S-Curve.
Progress Measurement | 3 | Compute Run Rate / Ask Rate & Forecast | 4 | PMO | EAC and forecast completion.
Progress Measurement | 4 | Publish Executive Dashboards | -> Governance | PMO / Analytics | Consumed from Data Lake.
Financial Progress | 1 | Budget Loading & AOP | 2 | Finance | SAP budget workflow (KB-031).
Financial Progress | 2 | Commitment on PR/PO | 3 | Finance | Budget reservation.
Financial Progress | 3 | CAPEX Booking on GRN/SES | 4 | Finance | Recognition independent of payment.
Financial Progress | 4 | Cash Flow / Payment Processing | -> Reporting | Finance | Advances & vendor payments.
Quality | 1 | Vendor Quality Assessment | 2 | Quality Team | Full lifecycle Needs SME Validation (KB-026).
Quality | 2 | Factory / Material Inspection | 3 | Quality Team | Dispatch clearance.
Quality | 3 | Site Inspection & Acceptance | 4 | Quality Team | Construction quality verification.
Quality | 4 | NCR Management | -> Construction | Quality Team | Corrective actions; vendor rating.
Safety | 1 | Permit to Work | 2 | Safety Team | Full workflow Needs SME Validation (KB-028).
Safety | 2 | Safety Observation / Near Miss | 3 | Site / Safety | Continuous during construction.
Safety | 3 | Incident / LTI Management | 4 | Safety Team | Escalation process pending.
Safety | 4 | Safety Audit | -> Governance | Safety Team | PPE & training compliance.
Commissioning | 1 | Mechanical Completion | 2 | Project / Commissioning | Confirmed conceptually (KB-032).
Commissioning | 2 | Testing & Trial Run | 3 | Commissioning | Detailed lifecycle pending.
Commissioning | 3 | Performance Guarantee Test | 4 | Commissioning | LD calculation Needs SME Validation (KB-033).
Commissioning | 4 | Acceptance / COD | -> Handover | Business / Operations | Transition to operations.

## Systems
Entity | Source_System | Table | Primary_Key
ENT_PROJECT | CapExpert | TBD - Technical Deep Dive | Enterprise Project ID - Business Key; physical field TBD (multi-system)
ENT_PROJECT | SAP ERP | TBD - Technical Deep Dive | SAP Project Definition - Business Key; physical field TBD (multi-system)
ENT_PROJECT | Primavera P6 | TBD - Technical Deep Dive | Primavera Project ID - Business Key; physical field TBD (multi-system)
ENT_CAPEX_NFA | CapExpert | TBD - Technical Deep Dive | NFA Number - Business Key; physical field TBD
ENT_AMENDMENT_NFA | CapExpert | TBD - Technical Deep Dive | Amendment NFA Number - Business Key; physical field TBD
ENT_CAPEX_PLAN | CapExpert | TBD - Technical Deep Dive | NFA Number + Period - Business Key; TBD
ENT_PROJECT_DEFINITION | SAP ERP | TBD - Technical Deep Dive | Project Definition No. - Business Key; TBD
ENT_WBS | Primavera P6 | TBD - Technical Deep Dive | WBS Code - Business Key; TBD (multi-system)
ENT_WBS | SAP ERP | TBD - Technical Deep Dive | WBS Element - Business Key; TBD (multi-system)
ENT_ACTIVITY | Primavera P6 | TBD - Technical Deep Dive | Activity ID - Business Key; TBD
ENT_BASELINE | Primavera P6 | TBD - Technical Deep Dive | Baseline ID - Business Key; TBD
ENT_MILESTONE | Primavera P6 | TBD - Technical Deep Dive | Milestone/Activity ID - Business Key; TBD
ENT_PRECON_ACTIVITY | PreCon360 | TBD - Technical Deep Dive | Pre-Con Activity ID - Business Key; TBD
ENT_STATUTORY_APPROVAL | PreCon360 | TBD - Technical Deep Dive | Approval ID - Business Key; TBD
ENT_LAND | PreCon360 | TBD - Technical Deep Dive | Land Parcel ID - Business Key; TBD
ENT_MDL | Autodesk CDE | TBD - Technical Deep Dive | MDL / Package ID - Business Key; TBD
ENT_ENGG_DOC | Autodesk CDE | TBD - Technical Deep Dive | Engineering Document Number - Business Key; TBD (multi-system)
ENT_REVISION | Autodesk CDE | TBD - Technical Deep Dive | Document No. + Revision - Business Key; TBD
ENT_PR | SAP ERP | TBD - Technical Deep Dive | PR Number - Business Key; TBD
ENT_RFP | SAP Ariba | TBD - Technical Deep Dive | RFP / Event ID - Business Key; TBD
ENT_TBER | SAP Ariba | TBD - Technical Deep Dive | Event ID - Business Key; TBD
ENT_COMMERCIAL_NFA | SAP Ariba (Ariba BTP) | TBD - Technical Deep Dive | Commercial NFA Number - Business Key; TBD
ENT_PO | SAP ERP | TBD - Technical Deep Dive | PO Number - Business Key; TBD
ENT_SO | SAP ERP | TBD - Technical Deep Dive | SO Number - Business Key; TBD
ENT_VENDOR | SAP ERP | TBD - Technical Deep Dive | Vendor Code - Business Key; TBD (multi-system)
ENT_VENDOR | SAP Ariba | TBD - Technical Deep Dive | Ariba Vendor ID - Business Key; TBD (multi-system)
ENT_MATERIAL | SAP ERP | TBD - Technical Deep Dive | Material Code - Business Key; TBD
ENT_GRN | SAP ERP | TBD - Technical Deep Dive | GRN Number - Business Key; TBD
ENT_SES | SAP ERP | TBD - Technical Deep Dive | SES Number - Business Key; TBD
ENT_INVOICE | SAP ERP | TBD - Technical Deep Dive | Invoice Number - Business Key; TBD
ENT_INVENTORY | SAP ERP | TBD - Technical Deep Dive | Material + Plant + Storage - Business Key; TBD
ENT_DPR | Primavera P6 / Business System | TBD - Technical Deep Dive | DPR ID - Business Key; TBD (source uncertain)
ENT_WPR | Primavera P6 / Business System | TBD - Technical Deep Dive | WPR ID - Business Key; TBD (source uncertain)
ENT_HUMAN_RESOURCE | Primavera P6 / BU System | TBD - Technical Deep Dive | Resource ID - Business Key; TBD
ENT_EQUIPMENT_RESOURCE | Primavera P6 / BU Spreadsheet | TBD - Technical Deep Dive | Equipment ID - Business Key; TBD (often offline)
ENT_NCR | Quality System (TBD) | TBD - Technical Deep Dive | NCR Number - Business Key; TBD (system not confirmed)
ENT_SAFETY_EVENT | Safety System (TBD) | TBD - Technical Deep Dive | Event ID - Business Key; TBD (system not confirmed)
ENT_RISK | Risk Register (TBD) | TBD - Technical Deep Dive | Risk ID - Business Key; TBD (often offline)
ENT_PHYSICAL_PROGRESS | Enterprise Data Lake | TBD - Technical Deep Dive | Derived - no native PK
ENT_FINANCIAL_PROGRESS | Enterprise Data Lake | TBD - Technical Deep Dive | Derived - no native PK
ENT_DASHBOARD | Enterprise Dashboards | TBD - Technical Deep Dive | Dashboard/Report ID - TBD

## BusinessRules
Rule_ID | Applies_To | Rule | Severity | Description
BR-001 | ENT_CAPEX_NFA / ENT_PROJECT | One CAPEX NFA generally represents one Project. | High | Rare exceptions combine projects (Confirmed).
BR-002 | ENT_PROJECT | Every project requires an approved CAPEX NFA. | Critical | Formal authorization prerequisite.
BR-003 | ENT_PROJECT / ENT_BUSINESS_UNIT | A project belongs to exactly one owning Business Unit. | Critical | Others are stakeholders only.
BR-004 | ENT_CAPEX_PLAN | Initiation financial metrics form the baseline; changes only via amendment. | High | Governs variance analysis.
BR-005 | ENT_CAPEX | CAPEX approval currency maintained in INR. | Medium | Foreign values converted to INR.
BR-006 | ENT_PROJECT | Project Manager/CPO assumes ownership after approval. | Medium | BU-governance dependent.
BR-007 | ENT_BASELINE | Every approved project maintains a Primavera schedule. | Critical | Planning prerequisite.
BR-008 | ENT_BASELINE | One approved baseline is the enterprise reference. | Critical | Official reporting reference.
BR-009 | ENT_ACTIVITY | Activities maintain predecessor-successor logic. | High | Enables critical path/float.
BR-010 | ENT_PRECON_ACTIVITY | Pre-Con activities originate from the approved checklist. | High | Traceable to initiation.
BR-011 | ENT_ACTIVITY | Activity progress is the basis for physical progress. | Critical | Enterprise reporting rule.
BR-012 | ENT_WBS | WBS standardization mandatory to enterprise levels; BUs may extend. | High | L2/L3 standard.
BR-015 | ENT_PRECON_ACTIVITY | Each activity has exactly one current 'Pending With' owner. | Medium | Single active accountability.
BR-017 | ENT_LAND | Land Acquisition maintains Required/Acquired/Balance. | Medium | Land readiness visibility.
BR-018 | ENT_STATUTORY_APPROVAL | Statutory approvals decomposed into structured hierarchies. | Medium | Category->Approval->Steps.
BR-019 | ENT_MDL / ENT_PACKAGE | Every engineering package maintains an MDL. | Critical | Engineering baseline.
BR-020 | ENT_ENGG_DOC | Engineering documents follow controlled revision management. | High | Change control.
BR-021 | ENT_REVISION | Review comments belong to a specific document revision. | Medium | Revision-scoped comments.
BR-022 | ENT_ENGG_DOC | Only approved RFC/GFC documents may be used for construction. | Critical | Execution gate.
BR-023 | ENT_ENGG_DOC | Engineering progress measured by document status. | High | Document-centric measurement.
BR-024 | ENT_MDL | MDL ownership jointly shared (vendor + owner engineering). | High | Co-ownership.
BR-025 | ENT_VENDOR | Standard procurement uses Approved Vendors. | High | Vendor master governance.
BR-026 | ENT_PR / ENT_RFP | Each PR produces one RFP. | Medium | 1:1 mapping.
BR-027 | ENT_TBER | Commercial evaluation begins only after technical evaluation. | Critical | Technical->Commercial principle.
BR-028 | ENT_PO | SAP is the System of Record for PR and PO. | Critical | Master data authority.
BR-029 | ENT_PO / ENT_SO | Procurement complete on PO/SO issuance. | High | Domain boundary.
BR-030 | ENT_COMMERCIAL_NFA | PO/SO governed through Commercial NFAs. | Critical | Commercial approval gate.
BR-031 | ENT_INTERNAL_ESTIMATE | Internal estimates remain confidential during bidding. | High | Commercial integrity.
BR-032 | ENT_ACTIVITY / ENT_ENGG_DOC | Construction execution uses approved RFC/GFC documents. | Critical | Engineering dependency.
BR-033 | ENT_ACTIVITY | Construction progress reported at activity level. | High | Reporting granularity.
BR-034 | ENT_PACKAGE | Package Owners accountable for validated progress. | High | Accountability.
BR-035 | ENT_MATERIAL | Free Issue Materials undergo reconciliation. | Medium | FIM control.
BR-036 | ENT_ACTIVITY | Construction completion = physical completion only. | High | Quality/commissioning downstream.
BR-039 | ENT_CAPEX | CAPEX recognized on GRN/SES, not payment. | Critical | Recognition rule.
BR-040 | ENT_FINANCIAL_PROGRESS | Annual financial progress measured against AOP. | High | Executive KPI.
BR-043 | ENT_DASHBOARD | Executive reporting compares performance against approved baselines. | High | Governance principle.
GBR-004 | ENT_ACTIVITY | Construction shall use only approved engineering deliverables. | Critical | Enterprise-wide.
GBR-005 | ENT_PR | Procurement follows technical evaluation before commercial. | Critical | Enterprise-wide.
GBR-008 | ENT_FINANCIAL_PROGRESS / ENT_CASH_FLOW | Financial Progress and Cash Flow are separate concepts. | High | Prevents conflation.
GBR-010 | ALL | Every major business object has a defined System of Record. | High | Data governance.
BR-DOA (KB-001) | ENT_DOA | Approval authority determined by CAPEX value/BU matrix. | Critical | Full matrix Needs SME Validation.

## BusinessGlossary
Acronym | Meaning
AOP | Annual Operating Plan
BIM | Building Information Modelling
BU | Business Unit
CAPEX | Capital Expenditure
CDE | Common Data Environment
COD | Commercial Operation Date
CPMAT | Central Project Management Assurance Team
DOA / TOA | Delegation of Authority
DPR | Daily Progress Report
EAC / PAC | (Estimated / Project) Cost at Completion
EPC | Engineering, Procurement & Construction
FIM | Free Issue Material
GFC | Good for Construction
GRN | Goods Receipt Note
IFR | Issued for Review (where applicable)
LC | Letter of Credit
LD | Liquidated Damages
LOD | Level of Development
LTI | Lost Time Injury
MDL | Master Deliverable List
NCR | Non-Conformance Report
NFA | Note for Approval
PMAT | Project Management Assurance Team
PO | Purchase Order
PR | Purchase Request
RFC | Release for Construction
RFP | Request for Proposal
SAP | Systems, Applications & Products
SES | Service Entry Sheet
SO | Service Order
TBER | Technical Bid Evaluation Report
WBS | Work Breakdown Structure
WPR | Weekly Progress Report